## Progress
Glocalization Survey — Progress
Cirque Corporation — English version
NO | Activity | Target | Completed | Progress % | Notes
1 | Survey Sheet preparation and upload | 1 | 1 |  | Filled and ready; awaiting upload
2 | Upload of regulations operating under Global standards | 0 | 0 | N/A | Cirque has no Global Version adoptions; not applicable
3 | Localized / Local version regulations revision | 72 | 69 |  | 69/72 ready as-is; 3 pending edits (IR severity matrix + Backup RTO/RPO)
4 | Localized / Local version regulations approval | 72 | 69 |  | Approval tracked in Cirque Inventory
5 | Localized / Local version regulations upload | 72 | 0 |  | None uploaded yet

## Cirque Inventory
Cirque ISMS Inventory (compliant with parent's IS-AMR04 Appendix 2 numbering)
Source: ISMS-Manual.docx v1.0 (effective 2026-05-08, A4, Arial 10pt, parent-compliant format)
Type: Localized = partially-applicable equivalent of a parent standard; Local = Cirque-independent (L-prefix)
NO | Cirque Compliant ID | Legacy ID | Category | Class | Standard / Form Name | Status | Type | Effective Date
1 | IS-APM02-CIRQ01-A00 | ISMS-Manual.docx | 00 Basic Policy & ISMS Manual | Manual | Cirque ISMS Master Manual (consolidated) | Exist & No corrections | Localized Version | 2026-05-08
2 | IS-APM01-CIRQ01-A00 | IS-CIRQ-P-001-G v2.0 | 00 Basic Policy & ISMS Manual | Regulation | Information Security Policy (Master) | Exist & No corrections | Localized Version | 2026-05-08
3 | IS-AHR01-CIRQ01-A00 | IS-CIRQ-P-002-G | 05 Human Security | Regulation | Roles, Responsibilities, and Authorities Policy | Exist & No corrections | Localized Version | 2025-07-01
4 | IS-LMR-CIRQ01-A00 | IS-CIRQ-P-003-G | 06 MS Support Process | Regulation | Risk Management Policy | Exist & No corrections | Local Version | 2025-07-01
5 | IS-AHR02-CIRQ01-A00 | IS-CIRQ-P-004-G | 05 Human Security | Regulation | Competence, Awareness, and Training Policy | Exist & No corrections | Localized Version | 2025-07-01
6 | IS-LMR-CIRQ02-A00 | IS-CIRQ-P-005-G | 06 MS Support Process | Regulation | Communication Policy | Exist & No corrections | Local Version | 2025-07-01
7 | IS-AMR04-CIRQ01-A00 | IS-CIRQ-P-006-G | 06 MS Support Process | Regulation | Documented Information Control Policy | Exist & No corrections | Localized Version | 2025-07-01
8 | IS-AAR01-CIRQ01-A00 | IS-CIRQ-P-007-G | 01 Information Management | Regulation | Asset Management Policy | Exist & No corrections | Localized Version | 2025-07-01
9 | IS-AIR01-CIRQ01-A00 | IS-CIRQ-P-008-G | 02 IT Security | Regulation | Access Control Policy | Exist & No corrections | Localized Version | 2025-07-01
10 | IS-AIR01-CIRQ02-A00 | IS-CIRQ-P-009-G | 02 IT Security | Regulation | Cryptography Policy | Exist & No corrections | Localized Version | 2025-07-01
11 | IS-AFR01-CIRQ01-A00 | IS-CIRQ-P-010-G | 03 Physical & Env Security | Regulation | Physical and Environmental Security Policy | Exist & No corrections | Localized Version | 2025-07-01
12 | IS-AIR01-CIRQ03-A00 | IS-CIRQ-P-011-G | 02 IT Security | Regulation | Operations Security Policy | Exist & No corrections | Localized Version | 2025-07-01
13 | IS-AAR05-CIRQ01-A00 | IS-CIRQ-P-012-G v1.1 | 01 Information Management | Regulation | Secure Development Policy (with mandatory threat modeling) | Exist & No corrections | Localized Version | 2026-05-08
14 | IS-ASR01-CIRQ01-A00 | IS-CIRQ-P-013-G | 04 Business Partner | Regulation | Supplier Relationships Policy | Exist & No corrections | Localized Version | 2025-07-01
15 | IS-AMG01-CIRQ01-A00 | IS-CIRQ-P-014-G | 06 MS Support Process | Regulation | Information Security Incident Management Policy | Exist & corrections | Localized Version | 2025-07-01
16 | IS-LIR-CIRQ01-A00 | IS-CIRQ-P-015-G | 02 IT Security | Regulation | Information Security Continuity Policy | Exist & No corrections | Local Version | 2025-07-01
17 | IS-AMR01-CIRQ01-A00 | IS-CIRQ-P-016-G | 06 MS Support Process | Regulation | Compliance Policy | Exist & No corrections | Localized Version | 2025-07-01
18 | IS-AAR02-CIRQ01-A00 | IS-CIRQ-P-017-G | 01 Information Management | Regulation | Privacy Policy (Global Core) | Exist & No corrections | Localized Version | 2025-07-01
19 | IS-AAR02-CIRQ02-A00 | IS-CIRQ-P-017-US | 01 Information Management | Regulation | Privacy Policy (US — CCPA/CPRA/UCPA) | Exist & No corrections | Localized Version | 2025-07-01
20 | IS-AAR06-CIRQ01-A00 | IS-CIRQ-P-017-ASIA | 01 Information Management | Regulation | Privacy Policy (Asia — Taiwan PDPA, China PIPL) | Exist & No corrections | Localized Version | 2025-07-01
21 | IS-AFR01-CIRQ02-A00 | IS-CIRQ-P-018-G | 03 Physical & Env Security | Regulation | Clear Desk and Clear Screen Policy | Exist & No corrections | Localized Version | 2025-07-01
22 | IS-AHR01-CIRQ02-A00 | IS-CIRQ-P-019-G | 05 Human Security | Regulation | Acceptable Use Policy | Exist & No corrections | Localized Version | 2025-07-01
23 | IS-AHR01-CIRQ03-A00 | IS-CIRQ-P-020-G | 05 Human Security | Regulation | Remote Work Policy | Exist & No corrections | Localized Version | 2025-07-01
24 | IS-AMR02-CIRQ01-A00 | IS-CIRQ-P-021-G | 06 MS Support Process | Regulation | Monitoring, Measurement, Analysis, and Evaluation Policy | Exist & No corrections | Localized Version | 2025-07-01
25 | IS-LMR-CIRQ03-A00 | IS-CIRQ-P-022-G | 06 MS Support Process | Regulation | Management Review Policy | Exist & No corrections | Local Version | 2025-07-01
26 | IS-AMR03-CIRQ01-A00 | IS-CIRQ-P-023-G | 06 MS Support Process | Regulation | Nonconformity and Corrective Action Policy | Exist & No corrections | Localized Version | 2025-07-01
27 | IS-LMR-CIRQ04-A00 | IS-CIRQ-P-024-G | 06 MS Support Process | Regulation | Continual Improvement Policy | Exist & No corrections | Local Version | 2025-07-01
28 | IS-LIR-CIRQ02-A00 | IS-CIRQ-P-025-G | 02 IT Security | Regulation | Artificial Intelligence Acceptable Use Policy | Exist & No corrections | Local Version | 2026-03-02
29 | IS-AAR01-CIRQ02-A00 | IS-CIRQ-P-026-G | 01 Information Management | Regulation | Data Classification Policy | Exist & No corrections | Localized Version | 2026-03-08
30 | IS-APM02-CIRQ02-A00 | IS-CIRQ-PR-001-G | 00 Basic Policy & ISMS Manual | Guideline | ISMS Scope Definition Procedure | Exist & No corrections | Localized Version | 2025-07-01
31 | IS-LMG-CIRQ01-A00 | IS-CIRQ-PR-002-G | 06 MS Support Process | Guideline | Information Security Risk Assessment Procedure | Exist & No corrections | Local Version | 2025-07-01
32 | IS-LMG-CIRQ02-A00 | IS-CIRQ-PR-003-G | 06 MS Support Process | Guideline | Information Security Risk Treatment Procedure | Exist & No corrections | Local Version | 2025-07-01
33 | IS-AHR02-CIRQ02-A00 | IS-CIRQ-PR-004-G | 05 Human Security | Guideline | Information Security Awareness and Training Procedure | Exist & No corrections | Localized Version | 2025-07-01
34 | IS-LMG-CIRQ03-A00 | IS-CIRQ-PR-005-G | 06 MS Support Process | Guideline | ISMS Communication Procedure | Exist & No corrections | Local Version | 2025-07-01
35 | IS-AMR04-CIRQ02-A00 | IS-CIRQ-PR-006-G | 06 MS Support Process | Guideline | Document Control Procedure (with parent's Section 7 workflow) | Exist & No corrections | Localized Version | 2026-05-08
36 | IS-AAR01-CIRQ03-A00 | IS-CIRQ-PR-007-G | 01 Information Management | Guideline | Asset Classification and Handling Procedure | Exist & No corrections | Localized Version | 2025-07-01
37 | IS-AIR01-CIRQ04-A00 | IS-CIRQ-PR-008-G | 02 IT Security | Guideline | Access Control Procedure | Exist & No corrections | Localized Version | 2025-07-01
38 | IS-AIR01-CIRQ05-A00 | IS-CIRQ-PR-009-G | 02 IT Security | Guideline | Privileged Access Management Procedure | Exist & No corrections | Localized Version | 2025-07-01
39 | IS-AIR01-CIRQ06-A00 | IS-CIRQ-PR-010-G | 02 IT Security | Guideline | Key Management Procedure | Exist & No corrections | Localized Version | 2025-07-01
40 | IS-AFR01-CIRQ03-A00 | IS-CIRQ-PR-011-G | 03 Physical & Env Security | Guideline | Physical Access Control Procedure | Exist & No corrections | Localized Version | 2025-07-01
41 | IS-AFR01-CIRQ04-A00 | IS-CIRQ-PR-012-G | 03 Physical & Env Security | Guideline | Equipment Security Procedure | Exist & No corrections | Localized Version | 2025-07-01
42 | IS-AIR01-CIRQ07-A00 | IS-CIRQ-PR-013-G | 02 IT Security | Guideline | Change Management Procedure | Exist & No corrections | Localized Version | 2025-07-01
43 | IS-AIR01-CIRQ08-A00 | IS-CIRQ-PR-014-G | 02 IT Security | Guideline | Backup and Restoration Procedure (RTO/RPO numbers being added) | Exist & corrections | Localized Version | 2026-05-31
44 | IS-AIR01-CIRQ09-A00 | IS-CIRQ-PR-015-G | 02 IT Security | Guideline | Logging and Monitoring Procedure | Exist & No corrections | Localized Version | 2025-07-01
45 | IS-AIR01-CIRQ10-A00 | IS-CIRQ-PR-016-G | 02 IT Security | Guideline | Network Security Management Procedure | Exist & No corrections | Localized Version | 2025-07-01
46 | IS-AAR05-CIRQ02-A00 | IS-CIRQ-PR-017-G v1.1 | 01 Information Management | Guideline | Secure Development Procedure (STRIDE threat modeling) | Exist & No corrections | Localized Version | 2026-05-08
47 | IS-AAR05-CIRQ03-A00 | IS-CIRQ-PR-018-G | 01 Information Management | Guideline | System Testing and Acceptance Procedure | Exist & No corrections | Localized Version | 2025-07-01
48 | IS-ASR01-CIRQ02-A00 | IS-CIRQ-PR-019-G | 04 Business Partner | Guideline | Supplier Security Review Procedure | Exist & No corrections | Localized Version | 2025-07-01
49 | IS-AMG01-CIRQ02-A00 | IS-CIRQ-PR-020-G | 06 MS Support Process | Guideline | Incident Response Procedure (Global Core) — severity matrix being added | Exist & corrections | Localized Version | 2026-05-31
50 | IS-AMG01-CIRQ03-A00 | IS-CIRQ-PR-020-US | 06 MS Support Process | Guideline | Incident Response Procedure (US Localized) — severity matrix being added | Exist & corrections | Localized Version | 2026-05-31
51 | IS-AMG01-CIRQ04-A00 | IS-CIRQ-PR-020-ASIA | 06 MS Support Process | Guideline | Incident Response Procedure (Asia Localized) — severity matrix being added | Exist & corrections | Localized Version | 2026-05-31
52 | IS-LIG-CIRQ01-A00 | IS-CIRQ-PR-021-G | 02 IT Security | Guideline | Business Continuity and Disaster Recovery Procedure | Exist & No corrections | Local Version | 2025-07-01
53 | IS-AMR02-CIRQ02-A00 | IS-CIRQ-PR-022-G | 06 MS Support Process | Guideline | ISMS Performance Monitoring Procedure | Exist & No corrections | Localized Version | 2025-07-01
54 | IS-AMR02-CIRQ03-A00 | IS-CIRQ-PR-023-G | 06 MS Support Process | Guideline | Internal Audit Procedure | Exist & No corrections | Localized Version | 2025-07-01
55 | IS-LMG-CIRQ04-A00 | IS-CIRQ-PR-024-G | 06 MS Support Process | Guideline | Management Review Procedure | Exist & No corrections | Local Version | 2025-07-01
56 | IS-AMR03-CIRQ02-A00 | IS-CIRQ-PR-025-G | 06 MS Support Process | Guideline | Corrective Action Procedure | Exist & No corrections | Localized Version | 2025-07-01
57 | IS-APM02-CIRQ01-A01A | IS-CIRQ-D-001-G v2.0 | 00 Basic Policy & ISMS Manual | Annex | ISMS Scope Document | Exist & No corrections | Localized Version | 2026-05-08
58 | IS-AMR06-CIRQ01-F01A | IS-CIRQ-D-002-G v1.2 | 06 MS Support Process | Form | Interested Parties and Their Requirements Register | Exist & No corrections | Localized Version | 2026-05-08
59 | IS-AMR01-CIRQ01-F01A | IS-CIRQ-D-003-G | 06 MS Support Process | Form | Legal Register (Global) | Exist & No corrections | Localized Version | 2025-07-30
60 | IS-AMR01-CIRQ01-F02A | IS-CIRQ-D-003-US | 06 MS Support Process | Form | Legal Register (US Localized) | Exist & No corrections | Localized Version | 2025-07-30
61 | IS-AMR01-CIRQ01-F03A | IS-CIRQ-D-003-ASIA | 06 MS Support Process | Form | Legal Register (Asia Localized) | Exist & No corrections | Localized Version | 2026-05-08
62 | IS-AHR01-CIRQ01-F01A | IS-CIRQ-D-004-G | 05 Human Security | Form | Information Security Roles Matrix | Exist & No corrections | Localized Version | 2025-07-01
63 | IS-LMR-CIRQ01-F01A | IS-CIRQ-D-005-G | 06 MS Support Process | Form | Risk Treatment Plan + Risk Assessment Register | Exist & No corrections | Local Version | 2025-07-01
64 | IS-APM02-CIRQ01-A02A | IS-CIRQ-D-006-G v2.0 | 00 Basic Policy & ISMS Manual | Annex | Statement of Applicability (ISO 27001:2022 + SOC 2:2017) | Exist & No corrections | Localized Version | 2026-05-08
65 | IS-LMR-CIRQ05-A00 | IS-CIRQ-D-007-G | 06 MS Support Process | Regulation | Information Security Objectives | Exist & No corrections | Local Version | 2025-07-01
66 | IS-LIR-CIRQ03-A00 | IS-CIRQ-D-008-G | 02 IT Security | Regulation | Business Continuity Plan | Exist & No corrections | Local Version | 2025-07-01
67 | IS-LIR-CIRQ04-A00 | IS-CIRQ-D-009-G | 02 IT Security | Regulation | Disaster Recovery Plan | Exist & No corrections | Local Version | 2025-07-01
68 | IS-AHR02-CIRQ01-F01A | IS-CIRQ-F-002-G | 05 Human Security | Form | Training Records Log | Exist & No corrections | Localized Version | 2025-07-01
69 | IS-AMR04-CIRQ01-F01A | IS-CIRQ-F-003-G | 06 MS Support Process | Form | Document Change Request Form | Exist & No corrections | Localized Version | 2025-07-01
70 | IS-AAR01-CIRQ01-F01A | IS-CIRQ-F-004-G | 01 Information Management | Form | Asset Register | Exist & No corrections | Localized Version | 2025-07-01
71 | IS-AMG01-CIRQ01-F01A | IS-CIRQ-F-005-G | 06 MS Support Process | Form | Incident Report Form | Exist & No corrections | Localized Version | 2025-07-01
72 | IS-AMR02-CIRQ01-F01A | IS-CIRQ-F-006-G | 06 MS Support Process | Form | Internal Audit Report Template | Exist & No corrections | Localized Version | 2025-07-01
73 | IS-LMR-CIRQ03-F01A | IS-CIRQ-F-007-G | 06 MS Support Process | Form | Management Review Meeting Minutes Template | Exist & No corrections | Local Version | 2025-07-01
74 | IS-AMR03-CIRQ01-F01A | IS-CIRQ-F-008-G | 06 MS Support Process | Form | Corrective Action Request (CAR) Form | Exist & No corrections | Localized Version | 2025-07-01
75 | IS-AMR03-CIRQ01-F01A-Record-2026-001 | CAR-2026-001 | 06 MS Support Process | Form | Populated CAR — Lenovo Trusted Supplier Program threat modeling response | Exist & No corrections | Localized Version | 2026-05-08
76 | IS-LMR-CIRQ06-F01A | (new 2026-05-08) | 06 MS Support Process | Form | Global Standard Revision Tracker (parent's IS-AMR04 alignment) | Exist & No corrections | Local Version | 2026-05-08

## Survey Sheet
Parent Reference (Global ISMS Standards) | [5 empty] | Cirque Response
NO | Parent Standard ID | Category | Division | Standard / Form Name | — | Status | Reason | Type | Cirque Standard Number | Plan Date
1 | IS-APM01-A04 | 00 Basic Policy & ISMS Manual | policy | Information Security Basic Policy |  | Exist & No corrections | Cirque maintains an equivalent master policy aligned to the parent's framework. | Localized Version | IS-APM01-CIRQ01-A00 | 2026-05-08
2 | IS-APM01-A01A | 00 Basic Policy & ISMS Manual | policy | (Public Version) Information Security Basic Policy |  | Exist & No corrections | Cirque master policy serves as both the internal master and source for any external-disclosure version derived on demand. | Localized Version | IS-APM01-CIRQ01-A00 | 2026-05-08
3 | IS-APM02-B09 | 00 Basic Policy & ISMS Manual | Manual | ISMS Manual |  | Exist & No corrections | Cirque consolidated all ISMS docs into a single 235-page A4 master manual on 2026-05-08. | Localized Version | IS-APM02-CIRQ01-A00 | 2026-05-08
4 | IS-APM02-A03C | 00 Basic Policy & ISMS Manual | Appendix(Statement) | ISMS Statement of Applicability (ISO 27001:2022) |  | Exist & No corrections | SoA fully populated covering all 93 ISO 27001:2022 Annex A controls + SOC 2 TSC mapping. | Localized Version | IS-APM02-CIRQ01-A02A | 2026-05-08
8 | IS-APM02-A02D | 00 Basic Policy & ISMS Manual | Appendix(Manual/Annex) | Customer Name Code (ISMS Manual Annex 1) |  | Exist & No corrections | Customer references appear throughout Cirque ISMS documentation; covered by master manual. | Localized Version | IS-APM02-CIRQ01-A00 | 2026-05-08
9 | IS-APM02-A01D | 00 Basic Policy & ISMS Manual | Appendix(Manual) | ISMS Glossary |  | Exist & No corrections | Definitions are embedded throughout the Cirque master manual; covered by master. | Localized Version | IS-APM02-CIRQ01-A00 | 2026-05-08
10 | IS-APM02-F01B | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Review Format |  | Exist & No corrections | Cirque MRM template defined and ready. | Localized Version | IS-LMR-CIRQ03-F01A | 2025-07-01
11 | IS-APM02-F02B | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Asset Management Table (Information) |  | Exist & No corrections | Cirque Asset Register exists and is operational; population from RMM/Intune is normal lifecycle. | Localized Version | IS-AAR01-CIRQ01-F01A | 2025-07-01
12 | IS-APM02-F03A | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Asset Management Table (Prototype) |  | Exist & No corrections | Prototype assets covered by Cirque Asset Register. | Localized Version | IS-AAR01-CIRQ01-F01A | 2025-07-01
13 | IS-APM02-F04C | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Auxiliary Assets |  | Exist & No corrections | Auxiliary assets covered by Cirque Asset Register. | Localized Version | IS-AAR01-CIRQ01-F01A | 2025-07-01
14 | IS-APM02-F05B | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger External Service Management Record Table |  | Exist & No corrections | External services managed via Cirque Supplier Policy + Supplier Review Procedure. | Localized Version | IS-ASR01-CIRQ01-A00 + IS-ASR01-CIRQ02-A00 | 2025-07-01
15 | IS-APM02-F06B | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Business Partner Management Table |  | Exist & No corrections | Business-partner register lives in Cirque Interested Parties (incl. Lenovo entry 2.11). | Localized Version | IS-AMR06-CIRQ01-F01A | 2026-05-08
16 | IS-APM02-F07A | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Project Management Table |  | Exist & No corrections | Project security covered by Cirque Secure Dev Policy + Procedure. | Localized Version | IS-AAR05-CIRQ01-A00 + IS-AAR05-CIRQ02-A00 | 2026-05-08
17 | IS-APM02-F08A | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Department Management Software Management Table |  | Exist & No corrections | Departmental software governed by Cirque Acceptable Use Policy + Supplier Relationships Policy + Intune deployment. | Localized Version | IS-AHR01-CIRQ02-A00 + IS-ASR01-CIRQ01-A00 | 2025-07-01
18 | IS-APM02-F09A | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Information Asset Availability Management Table |  | Exist & No corrections | Asset availability covered by Cirque Asset Register + Information Security Objectives KPIs. | Localized Version | IS-AAR01-CIRQ01-F01A + IS-LMR-CIRQ05-A00 | 2025-07-01
19 | IS-APM02-F10B | 00 Basic Policy & ISMS Manual | Appendix(Form) | ISMS Management Ledger Risk Tackle Matrix, KPI Dashboard, Action List, Opportunity Tackle Matrix |  | Exist & No corrections | Risk register, KPI dashboard, action list, and improvement matrix exist; ongoing population is normal lifecycle. | Localized Version | IS-LMR-CIRQ01-F01A + IS-LMR-CIRQ05-A00 | 2025-07-01
22 | IS-AAR01-A06 | 01 Information Management Regulations | Regulations | Information Management Regulation |  | Exist & No corrections | Information management covered by Cirque Asset Management Policy + Data Classification Policy + Asset Handling Procedure. | Localized Version | IS-AAR01-CIRQ01-A00 + IS-AAR01-CIRQ02-A00 + IS-AAR01-CIRQ03-A00 | 2025-07-01
23 | IS-AAR01-A01C | 01 Information Management Regulations | Appendix(Regulations) | Information Management Regulation Appendix |  | Exist & No corrections | Information management appendix combined with the Asset Classification & Handling Procedure. | Localized Version | IS-AAR01-CIRQ03-A00 | 2025-07-01
24 | IS-AAR02-A04 | 01 Information Management Regulations | Regulations | Personal Information Protection Policy |  | Exist & No corrections | Personal information protection covered by Cirque Privacy Policy (Global Core). | Localized Version | IS-AAR02-CIRQ01-A00 | 2025-07-01
25 | IS-AAR02-A01C | 01 Information Management Regulations | Appendix(Regulations) | Global Privacy Policy |  | Exist & No corrections | Same as NO 24. | Localized Version | IS-AAR02-CIRQ01-A00 | 2025-07-01
27 | IS-AAR02-A03C | 01 Information Management Regulations | Appendix(Regulations) | GDPR Privacy Policy |  | Exist & No corrections | Cirque Privacy Policy (Global Core) addresses GDPR principles. | Localized Version | IS-AAR02-CIRQ01-A00 | 2025-07-01
28 | IS-AAR02-A04C | 01 Information Management Regulations | Appendix(Regulations) | CCPA/CPRA Privacy Policy |  | Exist & No corrections | CCPA/CPRA + UCPA covered by Cirque Privacy Policy (US Localized). | Localized Version | IS-AAR02-CIRQ02-A00 | 2025-07-01
30 | IS-AAR04-A02 | 01 Information Management Regulations | Regulations | EU Personal Data Protection Policy |  | Exist & No corrections | EU personal data handling covered by Cirque Privacy Policy (Global Core). | Localized Version | IS-AAR02-CIRQ01-A00 | 2025-07-01
31 | IS-AAR05-B02 | 01 Information Management Regulations | Guidelines | Product Information Security Regulation |  | Exist & No corrections | Product information security covered by Cirque Secure Dev Policy v1.1 + Procedure v1.1 (mandatory threat modeling per Lenovo CAR-2026-001). | Localized Version | IS-AAR05-CIRQ01-A00 + IS-AAR05-CIRQ02-A00 | 2026-05-08
32 | IS-AAR06-A01 | 01 Information Management Regulations | Regulations | China Personal Information Protection Policy |  | Exist & No corrections | China PIPL covered by Cirque Privacy Policy (Asia) — addresses remote workers in China. | Localized Version | IS-AAR06-CIRQ01-A00 | 2025-07-01
36 | IS-AIR01-A07 | 02 IT Security | Regulations | Information System Security Regulation |  | Exist & No corrections | Information system security covered by Cirque Operations Security Policy + Access Control + supporting procedures. | Localized Version | IS-AIR01-CIRQ01-A00 + IS-AIR01-CIRQ03-A00 | 2025-07-01
37 | IS-AIR01-F01B | 02 IT Security | Appendix(Form) | Cloud Security Survey Sheet |  | Exist & No corrections | Cloud security questionnaires handled via Supplier Security Review Procedure. | Localized Version | IS-ASR01-CIRQ02-A00 | 2025-07-01
38 | IS-AIR01-A03D | 02 IT Security | Appendix(Guidelines) | Cloud Service Usage Guide |  | Exist & No corrections | Cloud usage governed by Supplier Policy + Acceptable Use Policy + Asset Management Policy. | Localized Version | IS-ASR01-CIRQ01-A00 + IS-AHR01-CIRQ02-A00 + IS-AAR01-CIRQ01-A00 | 2025-07-01
39 | IS-AIG01-A03 | 02 IT Security | standard | IT System Operation Standard |  | Exist & No corrections | IT system operation standard covered by Cirque Operations Security Policy + supporting procedures. | Localized Version | IS-AIR01-CIRQ03-A00 | 2025-07-01
40 | IS-AIG02-A04 | 02 IT Security | standard | PC Standard Environment Specification (Windows 10) |  | Exist & No corrections | Win 10 baseline managed via Intune; covered by Cirque Equipment Security Procedure. | Localized Version | IS-AFR01-CIRQ04-A00 | 2025-07-01
41 | IS-AIG03-A03 | 02 IT Security | Guidelines | Removable Storage Handling Procedure |  | Exist & No corrections | Removable storage handling covered by Cirque Clear Desk Policy + Acceptable Use Policy. | Localized Version | IS-AFR01-CIRQ02-A00 + IS-AHR01-CIRQ02-A00 | 2025-07-01
42 | IS-AIR03-A02 | 02 IT Security | Guidelines | PC Management Standard |  | Exist & No corrections | PC management covered by Cirque Equipment Security Procedure + Remote Work Policy. | Localized Version | IS-AFR01-CIRQ04-A00 + IS-AHR01-CIRQ03-A00 | 2025-07-01
43 | IS-AIR04-A00 | 02 IT Security | Regulations | CSIRT Regulation |  | Exist & corrections | CSIRT function covered by Cirque Incident Mgmt Policy + IR Procedures; severity matrix being added. | Localized Version | IS-AMG01-CIRQ01-A00 + IS-AMG01-CIRQ02-A00 | 2026-05-31
45 | IS-AIG04-A01 | 02 IT Security | Guidelines | System Backup & Recovery Specification |  | Exist & corrections | Backup & recovery covered by Cirque Backup Procedure; concrete RTO/RPO numbers being added. | Localized Version | IS-AIR01-CIRQ08-A00 | 2026-05-31
46 | IS-AIG05-A03 | 02 IT Security | Guidelines | User ID Management Procedure |  | Exist & No corrections | User ID management covered by Cirque Access Control Procedure + Privileged Access Management Procedure. | Localized Version | IS-AIR01-CIRQ04-A00 + IS-AIR01-CIRQ05-A00 | 2025-07-01
47 | IS-AIG06-A00 | 02 IT Security | standard | Network Architecture |  | Exist & No corrections | Network controls documented in Cirque Network Security Procedure. | Localized Version | IS-AIR01-CIRQ10-A00 | 2025-07-01
49 | IS-AIG08-A01 | 02 IT Security | standard | PC Standard Environment Specification (Windows 11) |  | Exist & No corrections | Win 11 baseline managed via Intune; covered by Cirque Equipment Security Procedure. | Localized Version | IS-AFR01-CIRQ04-A00 | 2025-07-01
50 | IS-AIG09-A01 | 02 IT Security | standard | ASM Vulnerability Response Procedure |  | Exist & No corrections | Vulnerability management covered by Cirque Network Security Procedure + Operations Security Policy. | Localized Version | IS-AIR01-CIRQ10-A00 + IS-AIR01-CIRQ03-A00 | 2025-07-01
51 | IS-AFR01-A08 | 03 Physical & Environmental Security | Regulations | Physical and Environmental Security Regulation |  | Exist & No corrections | Physical and environmental security covered by Cirque Physical Security Policy + Physical Access + Equipment Security procedures. | Localized Version | IS-AFR01-CIRQ01-A00 + IS-AFR01-CIRQ03-A00 + IS-AFR01-CIRQ04-A00 | 2025-07-01
52 | IS-ASG01-A04 | 04 Business Partner | Guidelines | Information Security Contract Guidance with Business Partners |  | Exist & No corrections | Contract security covered by Cirque Supplier Relationships Policy. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
53 | IS-ASG01-F01B | 04 Business Partner | Appendix(Form) | Request for Cooperation in Information Security Initiatives |  | Exist & No corrections | Supplier cooperation handled via Cirque Supplier Security Review Procedure. | Localized Version | IS-ASR01-CIRQ02-A00 | 2025-07-01
54 | IS-ASR01-A01C | 04 Business Partner | Appendix(Guidelines) | Information Security Management Guideline for Suppliers |  | Exist & No corrections | Supplier-facing requirements covered by Cirque Supplier Policy + Review Procedure. | Localized Version | IS-ASR01-CIRQ01-A00 + IS-ASR01-CIRQ02-A00 | 2025-07-01
55 | IS-ASR01-A05 | 04 Business Partner | Regulations | Business Partner Information Security Management Regulation |  | Exist & No corrections | Business partner security management covered by Cirque Supplier Policy + Supplier Review Procedure. | Localized Version | IS-ASR01-CIRQ01-A00 + IS-ASR01-CIRQ02-A00 | 2025-07-01
56 | IS-ASR01-F01D | 04 Business Partner | Appendix(Form) | Survey Sheet of Information Security for Suppliers |  | Exist & No corrections | Supplier security evaluation done via Cirque Supplier Security Review Procedure. | Localized Version | IS-ASR01-CIRQ02-A00 | 2025-07-01
57 | IS-ASR01-F02B | 04 Business Partner | Appendix(Form) | (To Supplier) Info Security Management Req (NORMAL) |  | Exist & No corrections | Tiered supplier requirements (NORMAL) covered by Cirque Supplier Policy. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
58 | IS-ASR01-F03B | 04 Business Partner | Appendix(Form) | (To Supplier) Info Security Management Req (HIGH) |  | Exist & No corrections | HIGH-tier supplier requirements covered by Cirque Supplier Policy. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
59 | IS-ASR01-F04B | 04 Business Partner | Appendix(Form) | (To Supplier) Info Security Management Req (Very HIGH) |  | Exist & No corrections | VERY HIGH-tier supplier requirements covered by Cirque Supplier Policy. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
60 | IS-ASR01-F05E | 04 Business Partner | Appendix(Form) | Cloud Security Assessment Request Form (Business Partner) |  | Exist & No corrections | Cloud-security assessment of business partners covered by Cirque Supplier Security Review Procedure. | Localized Version | IS-ASR01-CIRQ02-A00 | 2025-07-01
61 | IS-AHR01-A03 | 05 Human Security | Guidelines | Human Security Management Regulation |  | Exist & No corrections | Human security covered by Cirque Roles & Responsibilities Policy + Training Policy + AUP + Remote Work Policy. | Localized Version | IS-AHR01-CIRQ01-A00 + IS-AHR02-CIRQ01-A00 + IS-AHR01-CIRQ02-A00 + IS-AHR01-CIRQ03-A00 | 2025-07-01
63 | IS-AHR02-A02 | 05 Human Security | Regulations | Information Security Education and Training Management Regulation |  | Exist & No corrections | Education and training covered by Cirque Training Policy + Procedure + Records Log. | Localized Version | IS-AHR02-CIRQ01-A00 + IS-AHR02-CIRQ02-A00 + IS-AHR02-CIRQ01-F01A | 2025-07-01
64 | IS-AMR01-A05 | 06 MS Support Process | Regulations | Conformance Management Regulation |  | Exist & No corrections | Conformance management covered by Cirque Compliance Policy. | Localized Version | IS-AMR01-CIRQ01-A00 | 2025-07-01
65 | IS-AMR01-A01D | 06 MS Support Process | Appendix(Form) | List of ISMS Laws and Regulations (Management Ledger) |  | Exist & No corrections | Legal/regulatory register covered by Global + US + Asia legal registers. | Localized Version | IS-AMR01-CIRQ01-F01A + F02A + F03A | 2025-07-30
66 | IS-AMR02-A04 | 06 MS Support Process | Regulations | Internal Audit Management Regulation |  | Exist & No corrections | Internal audit covered by Cirque Internal Audit Procedure (annual cadence). | Localized Version | IS-AMR02-CIRQ03-A00 | 2025-07-01
67 | IS-AMR02-F01E | 06 MS Support Process | Appendix(Form) | Information Management Self Check Sheet |  | Exist & No corrections | Self-check function covered by Cirque ISMS Performance Monitoring Procedure + Internal Audit Procedure. | Localized Version | IS-AMR02-CIRQ02-A00 + IS-AMR02-CIRQ03-A00 | 2025-07-01
68 | IS-AMR03-A02 | 06 MS Support Process | Regulations | Corrective Action Management Regulation |  | Exist & No corrections | Corrective action management covered by Cirque Nonconformity Policy + Corrective Action Procedure + populated CAR-2026-001. | Localized Version | IS-AMR03-CIRQ01-A00 + IS-AMR03-CIRQ02-A00 | 2026-05-08
69 | IS-AMR03-F01B | 06 MS Support Process | Appendix(Form) | Corrective Action Form |  | Exist & No corrections | CAR form ready; populated CAR-2026-001 demonstrates operating effectiveness (Lenovo Trusted Supplier audit response). | Localized Version | IS-AMR03-CIRQ01-F01A | 2026-05-08
70 | IS-AMR03-F02B | 06 MS Support Process | Appendix(Form) | Corrective and Preventive Action Report |  | Exist & No corrections | Same artifact as NO 69; serves as both corrective and preventive-action record. | Localized Version | IS-AMR03-CIRQ01-F01A | 2026-05-08
71 | IS-AMG01-A02 | 06 MS Support Process | Procedure | Information Security Incident Handling Procedure |  | Exist & corrections | Incident handling covered by Cirque IR Procedures (Global / US / Asia); severity matrix and breach clocks being added. | Localized Version | IS-AMG01-CIRQ02-A00 + CIRQ03-A00 + CIRQ04-A00 | 2026-05-31
72 | IS-AMG01-F01A | 06 MS Support Process | Appendix(Form) | Security Incidents Record |  | Exist & No corrections | Incident report form covered by Cirque Incident Report Form. | Localized Version | IS-AMG01-CIRQ01-F01A | 2025-07-01
73 | IS-AMR04-A06 | 06 MS Support Process | Regulations | ISMS Standard Management Regulation |  | Exist & No corrections | ISMS Standard Management covered by Cirque Document Information Control Policy + Procedure (incorporates parent's IS-AMR04 Section 7 workflow). | Localized Version | IS-AMR04-CIRQ01-A00 + IS-AMR04-CIRQ02-A00 | 2026-05-08
74 | IS-AMR04-A01I | 06 MS Support Process | Appendix(Regulations) | Company-wide ISMS Standard Documents List & Establishing Departments |  | Exist & No corrections | Company-wide standards list = master manual TOC + Glocalization mapping + Global Standard Revision Tracker. | Localized Version | ISMS-Manual.docx + IS-LMR-CIRQ06-F01A | 2026-05-08
75 | IS-AMR04-F01A | 06 MS Support Process | Appendix(Regulations) | ISMS Standard Format |  | Exist & No corrections | ISMS standard format covered by Cirque Document Change Request Form. | Localized Version | IS-AMR04-CIRQ01-F01A | 2025-07-01
76 | IS-AMR05-A06 | 06 MS Support Process | Regulations | ISMS Records Management Regulation |  | Exist & No corrections | Records management covered by Cirque Document Info Control Policy + Procedure. | Localized Version | IS-AMR04-CIRQ01-A00 + IS-AMR04-CIRQ02-A00 | 2025-07-01
77 | IS-AMR06-B01 | 06 MS Support Process | Regulations | ISMS Customer Requirements Management Regulation |  | Exist & No corrections | Customer requirements management covered by Cirque Interested Parties register + populated CAR-2026-001. | Localized Version | IS-AMR06-CIRQ01-F01A | 2026-05-08
78 | IS-xNDA-001 | 07 Form / NDA | Form | Confidentiality Covenant for Employee |  | Exist & No corrections | Employee confidentiality covered by HR employment contracts + Cirque Acceptable Use Policy. | Localized Version | IS-AHR01-CIRQ02-A00 | 2025-07-01
79 | IS-xNDA-002 | 07 Form / NDA | Form | Confidentiality Pledge for Information Security (Temporary Employee) |  | Exist & No corrections | Temporary employee confidentiality covered by HR contracting + Cirque Acceptable Use Policy. | Localized Version | IS-AHR01-CIRQ02-A00 | 2025-07-01
80 | IS-xNDA-003 | 07 Form / NDA | Form | Confidentiality Pledge for Information Security (Business Partner Employee) |  | Exist & No corrections | Vendor employee confidentiality covered by Cirque Supplier Policy + executed vendor NDAs. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
81 | IS-xNDA-004 | 07 Form / NDA | Form | Confidentiality Covenant Specific Project (Employee) |  | Exist & No corrections | Project-specific employee confidentiality covered by HR employment contract + Cirque Acceptable Use Policy. | Localized Version | IS-AHR01-CIRQ02-A00 | 2025-07-01
82 | IS-xNDA-005 | 07 Form / NDA | Form | Confidentiality Pledge for Specific Project (Temporary Employee) |  | Exist & No corrections | Project-specific temp confidentiality covered by HR contracting + Cirque Acceptable Use Policy. | Localized Version | IS-AHR01-CIRQ02-A00 | 2025-07-01
83 | IS-xNDA-006 | 07 Form / NDA | Form | Confidentiality Pledge for Specific Project (Business Partner Employee) |  | Exist & No corrections | Project-specific vendor confidentiality covered by Cirque Supplier Policy + executed vendor NDAs. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
84 | IS-xNDA-007 | 07 Form / NDA | Form | Information Security Agreement for Business Partner |  | Exist & No corrections | Vendor information-security agreements executed via existing supplier-contract process. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01
85 | IS-xNDA-008 | 07 Form / NDA | Form | Information Security Pledge for Specific Project (Business Partner) |  | Exist & No corrections | Project-scoped vendor confidentiality covered by Cirque Supplier Policy + executed vendor NDAs. | Localized Version | IS-ASR01-CIRQ01-A00 | 2025-07-01